## How to Use
Document 26 — Validation Timing Checklist
How to use this workbook. It is the tick-list for document 25, the Validation Timing Guide: one row for every check at every gate, in build order, and a log for re-validation after the build. Document 25 says why and how; this workbook is where you mark it done.
THE TABS
| Gate Summary | One line per gate: how many checks, how many passed, failed or still to go, and the gate’s status. All formulas. Click a gate code to jump to it.
| Build Checklist | Ten gates, G0 to G9, and 76 checks in build order. This is the tab you fill in.
| Re-validation Log | One row per event after the build — a reload, a measure edit, a changed visual. Pick the Event and the tab tells you what to re-run.
| Triggers | The eleven events from document 25 Table 4.1, with what each requires. Reference only; the Re-validation Log reads from it.
RECORDING THE INITIAL BUILD
1 | Work on the Build Checklist from the top. Do not start a gate’s work until the gate before it reads PASSED on the Gate Summary tab.
2 | For each row, set Result (Pass, Fail, N/A or Not run), the Date, and Checked by. Put the number you saw in Observed value — “330,080 staged / 330,080 loaded”, not “ok”.
3 | When a row carries a Suite number, the column beside it says “Yes — check n”. Record that result in document 22 as well, on the Check Results tab, against the same check. Doc 22 is the formal record of the seventeen; this workbook is the working tick-list. The Procedure column on the same row names the step-by-step document for that check in docs/validation/ — open it if you have not run the check before.
4 | G5 and G8 are the two passes. G5 ends with doc 22 Run 1 reading INCOMPLETE — 5 not recorded; G8 ends with it reading PASS. Both are rows here, so the checklist cannot be completed while doc 22 disagrees.
5 | A Fail stops the gate. The Gate Summary reads BLOCKED until the row is fixed and re-recorded as Pass. Log the failure on the doc 22 Failure Log as well.
WHAT THE GATE STATUS MEANS
| PASSED | Every row in the gate is Pass or N/A. Start the next gate.
| OPEN — n to go | Rows still at Not run or blank. The number is how many.
| BLOCKED | At least one row is Fail. Nothing downstream of this gate should be built on it.
| All: COMPLETE | The bottom summary line: every row in every gate is Pass or N/A. The initial build is validated.
AFTER THE BUILD
1 | When one of the Triggers happens, add a row to the Re-validation Log with the date and the Event.
2 | What to re-run and the Doc 22 Trigger fill themselves in. Run those checks, then record the Result — and the Run ID if you started a new run in document 22.
3 | Something not on the list? Type it in Event anyway; What to re-run reads “not a listed event”. Add it to the Triggers tab if it will happen again.
RULES
• | N/A needs a reason in Observed value / notes. Skipped is not N/A — leave it as Not run.
• | To add a check, insert a row inside the gate on the Build Checklist and set its Gate code in column A. The Gate Summary counts it automatically — rows up to 600 are covered.
• | Do not type on the Gate Summary tab, or over the formula columns: Also record in doc 22 on the Build Checklist, and What to re-run and Doc 22 Trigger on the Re-validation Log.
WHERE THIS COMES FROM
| Document 25 | Validation Timing Guide — every gate, check and trigger on these tabs is taken from it.
| Document 22 | Validation and QA Results — the formal record of the seventeen suite checks.
| Document 21 | Development Checklist — the build tasks. Its phases map to the gates: G0 = Phases 0–1, G1 = 2, G2 = 3, G3 = 4, G4 = 5, G5 = 6, G6 = 7, G7 and G8 = 8, G9 = 9.
| docs/validation/ | One step-by-step procedure per suite check, V01 to V17, in .docx and .xlsx. The Procedure column on the Build Checklist names the one that covers each row.

## Gate Summary
Gate Summary — the initial build, gate by gate
Every figure here is a formula counting the Result column on the Build Checklist tab. Do not type on this tab. A gate is PASSED when all its rows are Pass or N/A; start the next gate only then.
Gate | Name | Run it | Checks | Pass | Fail | N/A | Not yet | Gate status | Doc 25
G0 | Repository and environment | Before any build step | [6 empty] | §3.1
G1 | Warehouse | After each SQL script, before the next | [6 empty] | §3.2
G2 | Power Query sources | After each source query | [6 empty] | §3.3
G3 | Model structure | After relationships and configuration, before any measure | [6 empty] | §3.4
G4 | Measures | As each measure folder closes | [6 empty] | §3.5
G5 | MODEL PASS | Before publishing the model | [6 empty] | §3.6
G6 | Publish and bind | After publishing the model | [6 empty] | §3.7
G7 | Report build | As each report page is finished | [6 empty] | §3.8
G8 | REPORT PASS | Before publishing each report | [6 empty] | §3.9
G9 | Packaging | Before the final push | [6 empty] | §3.10
All | Initial build

## Build Checklist
Build Checklist — every check at every gate, in build order
The recording companion to document 25. Work down the gates in order and set Result on every row; the Gate Summary tab counts itself from this column. A row with a Suite number is also recorded in document 22 against the same check. A gate is PASSED when every row is Pass or N/A. The Procedure column names the step-by-step document for that check in docs/validation/ — one file per check, V01 to V17.
Gate | Ref | Check | Pass when | Where | Suite # | Also record in doc 22 | Result | Date | Checked by | Observed value / notes | Procedure
G0 — REPOSITORY AND ENVIRONMENT · Before any build step · doc 25 §3.1
G0 | G0.01 | .gitignore committed before the first file | The first commit already contains .gitignore | Doc 00 §4.3 |  |  | Not run
G0 | G0.02 | Clone in place | git status runs from X:\retail-sector-health with a clean working tree | Doc 00 §5 |  |  | Not run
G0 | G0.03 | Environment matches the verified build | SSMS 22 connects to BRUNO\MSSQLSERVER01; versions match doc 02 Table 2.1 | Doc 02 §2.1 |  |  | Not run
G1 — WAREHOUSE · After each SQL script, before the next · doc 25 §3.2
G1 | G1.01 | sql/01 create database | sys.schemas returns stg and dw | sql/01 header |  |  | Not run
G1 | G1.02 | sql/02 staging table | Final SELECT returns approximately 330,080 rows | sql/02 header |  |  | Not run
G1 | G1.03 | sql/03 profiling queries | Five result sets read and noted in doc 21 | sql/03 header; doc 02 §5.5 |  |  | Not run
G1 | G1.04 | sql/04 dimensions | Each dimension has rows and no duplicate business key | sql/04 header |  |  | Not run
G1 | G1.05 | sql/05 fact and load procedure | Staged-versus-loaded reconciliation shows no unexplained gap | sql/05 header | 1 |  | Not run |  |  |  | V01
G1 | G1.06 | sql/06 item lifecycle | No NULL lifecycle column for an item with movement; MAX(LastSeenDateKey) = MAX(DateKey) | sql/06 header; doc 25 §3.2 | 12 |  | Not run |  |  |  | V12
G1 | G1.07 | sql/07 indexes | sys.indexes shows the columnstore index on dw.FactItemMovement | sql/07 header |  |  | Not run
G1 | G1.08 | sql/08 presentation views | SELECT TOP 10 * FROM dw.vw_ItemMovement returns resolved attributes | sql/08 header |  |  | Not run
G2 — POWER QUERY SOURCES · After each source query · doc 25 §3.3
G2 | G2.01 | Discovery query, run once | Returned codes reconcile with doc 02 Table 3.1; load then disabled | Doc 02 §3.4 |  |  | Not run
G2 | G2.02 | FactSectorSales | One row per month for 44X72 from pStartPeriod through the latest month Census has published, no gap | Doc 02 §3.5 | 2 |  | Not run |  |  |  | V02
G2 | G2.03 | FactMacro | Nine SeriesId values, each with a monthly series | Doc 02 §4.3 |  |  | Not run
G2 | G2.04 | DimCategory | Referential coverage query returns zero rows | Doc 02 §6.5 | 5 |  | Not run |  |  |  | V05
G2 | G2.05 | DimItem merge | No blank BeverageClass; unmatched types show as Unmapped | Doc 02 §6.3 |  |  | Not run
G2 | G2.06 | Every query | No key= literal; pCensusKey and pRefMappingsPath used only as parameters | Doc 02 §3.1, §6.1 |  |  | Not run
G3 — MODEL STRUCTURE · After relationships and configuration, before any measure · doc 25 §3.4
G3 | G3.01 | Auto-detected relationships removed | Only the seven relationships of doc 02 §7.2 exist | Doc 02 §7 |  |  | Not run
G3 | G3.02 | Model view against Figure 7.1 | Seven lines, all one-to-many, single-direction, on the right columns | Doc 02 Figure 7.1 |  |  | Not run
G3 | G3.03 | Date relationship integrity | No blank DimDate row — DAX query returns 0 | Doc 25 §3.4 | 6 |  | Not run |  |  |  | V06
G3 | G3.04 | Model configuration | Date table marked; sort-by columns set; keys hidden; Do Not Summarize | Doc 02 §7.3 |  |  | Not run
G4 — MEASURES · As each measure folder closes · doc 25 §3.5
G4 | G4.01 | Folder 01 Macro closes | CPI Index for a known month matches FRED CPIAUCSL | Doc 02 Table 8.2; doc 25 §3.5 |  |  | Not run
G4 | G4.02 | Folder 02 Sector closes | Census 452 matches FRED MRTSSM452USS within rounding; category gaps recorded | Doc 02 Table 8.2; doc 25 §3.5 | 3, 4 |  | Not run |  |  |  | V03, V04
G4 | G4.03 | Folder 03 Micro closes | Total Cases equals SUM(TotalMovement) in SQL; Return Rows non-zero | Doc 02 Table 8.2; doc 25 §3.5 | 11 |  | Not run |  |  |  | V11
G4 | G4.04 | Folder 04 Cross-Tier closes | National Liquor Stores Real Sales moves with RRSFS | Doc 02 Table 8.2 |  |  | Not run
G4 | G4.05 | Folder 05 Channel closes | 2019 baseline query returns no rows for any class, type and year; national series direction recorded | Doc 02 Table 8.2; doc 25 §3.5 | 9, 10 |  | Not run |  |  |  | V09, V10
G4 | G4.06 | Folder 06 Elasticity closes | Observation Count non-zero and plausible | Doc 02 Table 8.2; doc 25 §3.5 |  |  | Not run
G4 | G4.07 | Folder 07 Rotation closes | Rate Sensitivity Beta negative for 441, 442 and 444 | Doc 02 Table 8.2; doc 25 §3.5 |  |  | Not run
G4 | G4.08 | Folder 08 Assortment closes | Cohort Size by year sums to the DimItem row count; Cumulative Cases % is exactly 1 at the lowest rank | Doc 02 Table 8.2; doc 25 §3.5 | 13, 14 |  | Not run |  |  |  | V13, V14
G4 | G4.09 | Folder 09 Supplier closes | Supplier HHI between 0 and 10,000 | Doc 02 Table 8.2; doc 25 §3.5 |  |  | Not run
G4 | G4.10 | Folder 10 Seasonality closes | The twelve seasonal factors average approximately 1.00 | Doc 02 Table 8.2; doc 25 §3.5 |  |  | Not run
G5 — MODEL PASS · Before publishing the model · doc 25 §3.6
G5 | G5.01 | Check 1 — final run on the finished model | Staged versus loaded: zero difference or every dropped row explained | Doc 02 §9; doc 22 Check Catalog | 1 |  | Not run |  |  |  | V01
G5 | G5.02 | Check 2 — final run on the finished model | No gap in the 44X72 monthly sequence | Doc 02 §9; doc 22 Check Catalog | 2 |  | Not run |  |  |  | V02
G5 | G5.03 | Check 3 — final run on the finished model | Category gaps to 44X72 recorded with their reason | Doc 02 §9; doc 22 Check Catalog | 3 |  | Not run |  |  |  | V03
G5 | G5.04 | Check 4 — final run on the finished model | Census 452 within rounding of FRED MRTSSM452USS | Doc 02 §9; doc 22 Check Catalog | 4 |  | Not run |  |  |  | V04
G5 | G5.05 | Check 5 — final run on the finished model | Coverage query returns zero rows | Doc 02 §9; doc 22 Check Catalog | 5 |  | Not run |  |  |  | V05
G5 | G5.06 | Check 6 — final run on the finished model | No blank row in DimDate | Doc 02 §9; doc 22 Check Catalog | 6 |  | Not run |  |  |  | V06
G5 | G5.07 | Check 9 — final run on the finished model | 2019 baselines return a value for every class, type and year (V09 Parts 1 and 3) | Doc 02 §9; doc 22 Check Catalog | 9 |  | Not run |  |  |  | V09
G5 | G5.08 | Check 10 — final run on the finished model | National series move with the local on-premise collapse; direction and months recorded | Doc 02 §9; doc 22 Check Catalog | 10 |  | Not run |  |  |  | V10
G5 | G5.09 | Check 11 — final run on the finished model | Return Rows non-zero | Doc 02 §9; doc 22 Check Catalog | 11 |  | Not run |  |  |  | V11
G5 | G5.10 | Check 12 — final run on the finished model | MAX(LastSeenDateKey) equals MAX(DateKey) | Doc 02 §9; doc 22 Check Catalog | 12 |  | Not run |  |  |  | V12
G5 | G5.11 | Check 13 — final run on the finished model | Cohort Size summed across CohortYear equals the DimItem row count | Doc 02 §9; doc 22 Check Catalog | 13 |  | Not run |  |  |  | V13
G5 | G5.12 | Check 14 — final run on the finished model | Cumulative Cases % is exactly 100% at the lowest rank, unfiltered and under each year and item type | Doc 02 §9; doc 22 Check Catalog | 14 |  | Not run |  |  |  | V14
G5 | G5.13 | Doc 22 Run 1 Outcome | Reads INCOMPLETE — 5 not recorded, with zero Blocking failures (an Advisory failure adds “· n Advisory failing”) | Doc 22 Run Summary |  |  | Not run
G6 — PUBLISH AND BIND · After publishing the model · doc 25 §3.7
G6 | G6.01 | First refresh in the Service | All four sources refresh: SQL Server and RefMappings.xlsx through the gateway, FRED and Census without it | Doc 02 §10 |  |  | Not run
G6 | G6.02 | Refresh schedule | Set on the semantic model, twice weekly | Doc 02 §10 |  |  | Not run
G6 | G6.03 | R1 file created | Live-connection indicator shown; Fields pane read-only | Doc 02 §10 step 8 | 17 |  | Not run |  |  |  | V17
G6 | G6.04 | R2 file created | Live-connection indicator shown; Fields pane read-only | Doc 02 §10 step 8 | 17 |  | Not run |  |  |  | V17
G6 | G6.05 | R3 file created | Live-connection indicator shown; Fields pane read-only | Doc 02 §10 step 8 | 17 |  | Not run |  |  |  | V17
G7 — REPORT BUILD · As each report page is finished · doc 25 §3.8
G7 | G7.01 | R1 theme applied and verified | Three theme checks pass before the first visual | Doc 15 §3.3 |  |  | Not run
G7 | G7.02 | R1 Page 1 finished | Multi-measure visuals 1.5, 1.6, 1.7 and narrative 1.8 checked | Doc 25 Table 3.7 | 7, 8 |  | Not run |  |  |  | V07, V08
G7 | G7.03 | R1 Page 2 finished | Dollar series only — built to spec | Doc 25 Table 3.7 |  |  | Not run
G7 | G7.04 | R1 Page 3 finished | Multi-measure, case and difference visuals, baselines, Return Rows card and national-series narrative checked | Doc 25 Table 3.7 | 7, 8, 9, 10, 11 |  | Not run |  |  |  | V07, V08, V09, V10, V11
G7 | G7.05 | R2 theme applied and verified | Three theme checks pass before the first visual | Doc 15 §3.3 |  |  | Not run
G7 | G7.06 | R2 Page 1 finished | Dual axis, case visuals, slopes with Observation Count checked | Doc 25 Table 3.7 | 7, 8, 15 |  | Not run |  |  |  | V07, V08, V15
G7 | G7.07 | R2 Page 2 finished | Dual axis, case visuals, item-type 2019 baselines 5.3, 5.6, 5.8 checked | Doc 25 Table 3.7 | 7, 8, 9 |  | Not run |  |  |  | V07, V08, V09
G7 | G7.08 | R2 Page 3 finished | Share Transfer 6.6 on one axis; slope visuals 6.8 and 6.9 carry Observation Count | Doc 25 Table 3.7 | 7, 15 |  | Not run |  |  |  | V07, V15
G7 | G7.09 | R3 theme applied and verified | Three theme checks pass before the first visual | Doc 15 §3.3 |  |  | Not run
G7 | G7.10 | R3 Page 1 finished | Dual axis, case and item-count visuals, Pareto reaches exactly 100% | Doc 25 Table 3.7 | 7, 8, 14 |  | Not run |  |  |  | V07, V08, V14
G7 | G7.11 | R3 Page 2 finished | 2017 cohort excluded or labelled on every visual 8.2–8.8; 8.6 on one axis; no dollar measure | Doc 25 Table 3.7 | 7, 8, 16 |  | Not run |  |  |  | V07, V08, V16
G7 | G7.12 | R3 Page 3 finished | Dual axis and case visuals 9.1–9.8 checked | Doc 25 Table 3.7 | 7, 8 |  | Not run |  |  |  | V07, V08
G7 | G7.13 | R3 Page 4 finished | Adjusted vs Raw on one axis; case visuals 10.1–10.8 and method note checked | Doc 25 Table 3.7 | 7, 8 |  | Not run |  |  |  | V07, V08
G7 | G7.14 | Drillthrough page built | Item Detail page carries cases only — no dollar measure | Doc 15 §8.3 | 8 |  | Not run |  |  |  | V08
G7 | G7.15 | Tooltip page built and assigned | Tooltip page shows cases only and is used on no dollar visual | Doc 15 §8.4 | 8 |  | Not run |  |  |  | V08
G7 | G7.16 | Cross-report wiring | Date slicer synced on every page, other slicers unsynced; Reset bookmark and button on every page; drillthrough from 3.6 opens Item Detail filtered | Doc 15 §8 |  |  | Not run
G7 | G7.17 | Accessibility pass | Alt text, tab order, no meaning by colour alone, 4.5:1 text contrast, descriptive titles — on every page of each report | Doc 15 §9 |  |  | Not run
G8 — REPORT PASS · Before publishing each report · doc 25 §3.9
G8 | G8.01 | R1 report pass | Checks 7, 8 and 17 recorded for R1 in doc 22 Reports covered; 9, 10 and 11 updated from Page 3 | Doc 15 §10 | 7, 8, 9, 10, 11, 17 |  | Not run |  |  |  | V07, V08, V09, V10, V11, V17
G8 | G8.02 | R1 published | Published only with zero Blocking failures | Doc 15 §10 |  |  | Not run
G8 | G8.03 | R2 report pass | Checks 7, 8, 15 and 17 recorded for R2 in Reports covered; 9 updated from Page 2 | Doc 15 §10 | 7, 8, 9, 15, 17 |  | Not run |  |  |  | V07, V08, V09, V15, V17
G8 | G8.04 | R2 published | Published only with zero Blocking failures | Doc 15 §10 |  |  | Not run
G8 | G8.05 | R3 report pass | Checks 7, 8, 16 and 17 recorded for R3 in Reports covered; 14 updated from Page 1 | Doc 15 §10 | 7, 8, 14, 16, 17 |  | Not run |  |  |  | V07, V08, V14, V16, V17
G8 | G8.06 | R3 published | Published only with zero Blocking failures | Doc 15 §10 |  |  | Not run
G8 | G8.07 | Doc 22 Run 1 Outcome | Reads PASS — all seventeen recorded (PASSED WITH FAILURES only with a logged Advisory failure) | Doc 22 Run Summary |  |  | Not run
G9 — PACKAGING · Before the final push · doc 25 §3.10
G9 | G9.01 | Doc 00 §14 checklist | Run end to end | Doc 00 §14 |  |  | Not run
G9 | G9.02 | Repository search | No .csv, no key=, no first six characters of the key | Doc 00 §12, §14 |  |  | Not run
G9 | G9.03 | Report PBIP folders | Report definition only, no TMDL — the reports are thin | Doc 00 §14 |  |  | Not run

## Re-validation Log
Re-validation Log — after the build
One row per event. Choose the Event; What to re-run and the doc 22 Trigger fill in from the Triggers tab. Record the result, and the doc 22 Run ID if the event started a run there.
Date | Event | What changed | What to re-run | Doc 22 Trigger | Result | Doc 22 Run ID | Checked by | Notes

## Triggers
Triggers — the events that call for re-validation
Document 25 Table 4.1. The Event list on the Re-validation Log reads from this tab; add a row here to make a new event selectable.
Event | What to re-run | Doc 22 Trigger
A fact table reloads with new data | sql/06 first if the county data moved; then the twelve data checks 1–6, 9–14 | Post fact-table reload
A measure is edited | That folder's closing check; every folder whose Depends on names it; any suite check naming it; then republish | Post measure change
A relationship or model setting changes | Figure 7.1 comparison; check 6; all ten folder closing checks; then the model pass | Ad hoc
RefMappings.xlsx is edited | Check 5; look for Unmapped in slicers; check 3 if IsAggregate changed | Ad hoc
Census changes its category set | Doc 02 §3.4 discovery; update Table 3.1 and RefMappings.xlsx; checks 5 and 3 | Ad hoc
A report visual is added or changed | Checks 7 and 8 on that page; any of 9, 11, 14, 15, 16 it carries; 17 | Post report change
A theme .json is edited | Re-apply the theme; the three theme checks in doc 15 §3.3 | Not recorded in doc 22
The model is republished | First refresh succeeds; check 17 on each report | Pre-publication
Before any push to GitHub | Search for key= and .csv | Not recorded in doc 22
A sql/04, 05 or 06 script is edited | sql/04 to 06 in order; checks 1, 12 and 13; then the rest of the twelve data checks | Ad hoc
A Power Query source query or parameter is edited | Checks 2, 4 and 6; then 3 and 5 | Ad hoc