## Checklist
U.S. Retail Sector Health — Development Checklist
Mark Done as Y, N or N/A. A task marked N/A is excluded from the totals. To add a task, insert a row anywhere inside the list and pick a value in "Needed For This Project" — the counts update on their own. To remove one, delete the whole row.
PROGRESS
Tasks in this checklist | 199 | counts every row with a value in column B
Not needed — marked N/A | 20 | out of scope for this project
Needed for this project | 179 | everything not marked N/A
Done | 8
Remaining | 171
Percent complete | 4.469% | of the tasks this project needs
Task | Needed For This Project | Done (Y,N,N/A) | Relevant Notes
PHASE 0 — REPOSITORY (document 00 §3 - §5, §8)
Create the GitHub account | No | N/A | Public is the point — a private portfolio repo cannot be reviewed. Doc 00 §4.1–4.2.
Create the public repo | Yes | Y
Add .gitignore BEFORE the first upload | Yes | Y | A file blocked by .gitignore was never tracked; one removed afterwards stays in history forever. Doc 00 §4.3.
Add LICENSE (MIT) | Yes | Y | Ticked at repo creation — GitHub writes the file.
Add CONTRIBUTING.md | Yes | Y | Content is doc 00 Appendix A.
Create the folder skeleton with a README in each folder | Yes | Y | Nine folders. README content is doc 00 Appendix C.
Clone the repository to the local drive | Yes | Y | Everything after this is saved inside the clone. Doc 00 §5.
Install GitHub Desktop | No | N/A | Used for the PBIP commit loop; the website handles document uploads.
Create optional .gitattributes for those who want to explicitly handle file line endings | Yes | Y
Enable the PBIP (Power BI Project) save format in Desktop | Yes |  | Preview feature. This is what makes DAX changes reviewable as diffs.
Add tools/Publish-ToRepo.ps1 and run it once with -WhatIf | Yes | Y | Copies finished files from the working folder into the right repo folders.
Fabric Git integration (workspace-level sync) | No | N/A | Requires Fabric capacity; this project is specified on Power BI Pro. Doc 00 §10 covers it as a future option.
Branch protection rules / required reviews | No | N/A | Single contributor. Doc 00 §9.5 does one branch round-trip for the demonstration.
GitHub Actions or other CI | No | N/A | Nothing to build or test automatically. A commit history is the artifact.
PHASE 1 — ENVIRONMENT (document 00 §6)
Install SQL Server 2025 Developer Edition | No | N/A | Already installed
Install SQL Server Management Studio 22 | No | N/A | Already installed
Install Power BI Desktop (64-bit) | No | N/A | Already installed
Confirm the Power BI Pro licence | Yes |  | Needed to publish and to create live connections. Not needed to build locally.
Request the Census API key | Yes |  | Free, arrives by email in minutes. api.census.gov/data/key_signup.html
Install the on-premises data gateway (personal mode) | Yes |  | AFTER publishing, not before. Doc 02 §10.
Setup local folder layout | Yes |  | The clone lives at the GitHub Desktop default path. Two folders sit outside it deliberately.
Azure Data Factory / Synapse pipelines | No | N/A | Ingestion is Power Query and T-SQL. No orchestration tool in scope.
Power BI dataflows (Gen1 or Gen2) | No | N/A | One model, one developer. A dataflow adds a layer with nothing to reuse it.
PHASE 2 — SOURCE DATA AND WAREHOUSE (document 02 §5)
Download the county CSV to C:\Data\RetailEconomics\ | Yes |  | OUTSIDE the repository. Never committed — the README links to data.gov instead.
Run sql/01_create_database.sql | Yes |  | Database plus the stg and dw schemas.
Run sql/02_staging_table.sql | Yes |  | All columns NVARCHAR, then BULK INSERT. Expect ~330,080 rows.
Run sql/03_profiling_queries.sql and record the results | Yes |  | Read-only. The cleansing choices in 04 follow from what this returns.
Run sql/04_dimensions.sql | Yes |  | DimSupplier, DimItem, DimDate. DimDate is MONTHLY.
Run sql/05_fact_and_proc.sql | Yes |  | Fact table and load procedure. Check the staged-versus-loaded reconciliation.
Run sql/06_item_lifecycle.sql | Yes |  | RE-RUN THIS AFTER EVERY RELOAD OF THE FACT TABLE. Derived columns go stale silently.
Run sql/07_indexes.sql | Yes |  | Index after loading, not before.
Run sql/08_presentation_views.sql | Yes |  | dw.vw_ItemMovement — the only object Power BI reads.
Build RefMappings.xlsx using NAMED TABLES | Yes |  | A sheet range shifts when a row is inserted; a named table does not. Doc 02 §6.1.
Commit the eight .sql scripts to sql/ | Yes |  | Running them in order on a clean instance must reproduce the warehouse.
Stored procedures for incremental load | No | N/A | Full reload is seconds on 330K rows. Doc 02 §5.7 has one load procedure and that is enough.
PHASE 3 — POWER QUERY (document 02 §3, §4, §6)
Create parameters pCensusKey, pStartPeriod, pEndPeriod | Yes |  | A parameter is what stops the source being classified as dynamic.
Build fnGetFredSeries as a reusable function | Yes |  | Build this before FactMacro — FactMacro invokes it once per series.
Build FactMacro (nine FRED series) | Yes
Build FactSectorSales (Census MARTS) | Yes |  | Web.Contents with RelativePath and Query, never a concatenated URL.
Build DimCategory from RefMappings.xlsx | Yes
Connect to SQL Server and select the VIEWS only | Yes |  | Do not select dw.DimItem directly — dw.vw_Item is the contract.
Merge the item type mappings into DimItem | Yes |  | Unmatched types become "Unmapped", not blank.
Confirm no API key literal appears in any query | Yes |  | Search the M and the PBIP text for "key=" before the first push.
Commit the .m files to powerquery/ | Yes |  | A readable mirror of the model, not the model itself.
Incremental refresh policy | No | N/A | Ten years of monthly data is small. Full refresh is simpler and cheaper to explain.
PHASE 4 — SEMANTIC MODEL (document 02 §7)
Create the _Measures table and hide its placeholder column | Yes |  | Holds all 79 measures. It has no relationships and that is correct.
Create the seven relationships | Yes |  | All one-to-many, single-direction, active. Check against Figure 7.1.
Compare Model view against Figure 7.1 before writing any measure | Yes |  | A wrong relationship raises no error — it returns plausible wrong numbers.
Delete any relationship Power BI auto-detected | Yes |  | Auto-detect is the most common source of an extra line nobody added.
Mark DimDate as a date table on DimDate[Date] | Yes |  | Without this, time intelligence is silently wrong.
Set sort-by-column (MonthName by MonthNumber, etc.) | Yes |  | Otherwise every month-ordered visual sorts alphabetically.
Hide foreign keys and technical columns from Report view | Yes |  | DateKey, SeriesId, CategoryCode, SupplierKey, ItemKey and the lifecycle keys.
Set summarisation to Do Not Summarize on numeric non-measures | Yes |  | A dragged CohortYear that becomes SUM(CohortYear) is hard to spot on a finished visual.
Set format strings at the model level | Yes |  | Given with each measure in §8. Not on individual visuals.
Create the ten display folders inside _Measures | Yes |  | Type the names exactly, leading number included.
Row-level security (RLS) roles | No | N/A | Public data, single audience. Nothing to restrict.
Calculation groups | No | N/A | Would help if the same time intelligence repeated across many measures; here the YoY pattern is explicit and readable.
Field parameters | No | N/A | Not in the report specification. Would change what doc 15 specifies.
Composite model / aggregations / DirectQuery | No | N/A | Import mode throughout. The data fits comfortably in memory.
PHASE 5 — MEASURES (document 02 §8, 79 total)
Folder 01 Macro (8 measures) | Yes |  | Close when CPI Index for a known month matches the FRED series page.
Macro Value | Yes
Macro Value PM | Yes
Macro Value PY | Yes
CPI Index | Yes
CPI YoY % | Yes
Fed Funds Rate | Yes
Consumer Sentiment | Yes
Macro Indexed to 100 | Yes
Folder 02 Sector (10 measures) | Yes |  | Close when Sector Sales for code 452 matches FRED MRTSSM452USS within rounding.
Sector Sales | Yes
Sector Sales PY | Yes
Sector Sales YoY % | Yes
Sector Sales 3M Avg | Yes
Sector Sales 12M Avg | Yes
Total Retail and Food Services | Yes
Share of Total Retail % | Yes
Real Sector Sales | Yes
Real Sector Sales YoY % | Yes
Nominal less Real YoY (pp) | Yes
Folder 03 Micro (12 measures) | Yes |  | Close when Total Cases unfiltered reconciles to the fact-table sum in SQL.
Retail Cases | Yes
Warehouse Cases | Yes
Transfer Cases | Yes
Total Cases | Yes
Retail Cases YoY % | Yes
Total Cases YoY % | Yes
Retail Share of Movement % | Yes
Transfer to Sales Ratio | Yes
Active Items | Yes
Active Suppliers | Yes
Top 10 Supplier Share % | Yes
Return Rows | Yes
Folder 04 Cross-Tier (6 measures) | Yes |  | Close when National Liquor Stores Real Sales moves with, not against, RRSFS.
National Liquor Stores Sales | Yes
National Liquor Stores Real Sales | Yes
National Liquor Stores Nominal YoY % | Yes
National Liquor Stores Real YoY % | Yes
Volume Gap vs National (pp) | Yes
Implied Price Contribution (pp) | Yes
Folder 05 Channel (9 measures) | Yes |  | Close when the 2019 baseline returns a value under every R1 Page 3 slicer combination.
Off-Premise Cases | Yes
On-Premise Cases | Yes
On-Premise Share % | Yes
Keg Cases | Yes
Keg Share % | Yes
On-Premise Share 2019 Baseline | Yes
On-Premise Share vs 2019 (pp) | Yes
On-Premise Cases vs 2019 Same Month % | Yes
Channel Divergence (pp) | Yes
Folder 06 Elasticity (12 measures) | Yes |  | Close when Observation Count is non-zero and plausible before any slope is trusted.
Unemployment Rate | Yes
Personal Saving Rate | Yes
Real Disposable Income | Yes
Real Disposable Income YoY % | Yes
Consumer Stress Index | Yes
Volume Stress Sensitivity | Yes
Volume Stress Correlation | Yes
Observation Count | Yes
Item Type Share % | Yes
Item Type Share 2019 Baseline | Yes
Item Type Share vs 2019 (pp) | Yes
Mix Shift Magnitude (pp) | Yes
Folder 07 Rotation (5 measures) | Yes |  | Close when Rate Sensitivity Beta lands negative for 441, 442 and 444.
E-commerce Share % | Yes
Department Store Share % | Yes
Warehouse Club Share % | Yes
Goods to Services Ratio | Yes
Rate Sensitivity Beta | Yes
Folder 08 Assortment (10 measures) | Yes |  | Close when Cumulative Cases % reaches exactly 100% at the lowest-ranked item.
New Items | Yes
Discontinued Items | Yes
Net Assortment Change | Yes
Cohort Size | Yes
Cohort Survival 12M % | Yes
Cohort Survival 24M % | Yes
Median Months Active | Yes
Item Rank by Volume | Yes
Cumulative Cases % | Yes
Items to 80% of Volume | Yes
Folder 09 Supplier (2 measures) | Yes |  | Close when Supplier HHI falls between 0 and 10,000.
Supplier HHI | Yes
Supplier Return Rate % | Yes
Folder 10 Seasonality (5 measures) | Yes |  | Close when the twelve Month Seasonal Factor values average to approximately 1.00.
Month Seasonal Factor | Yes
Seasonally Adjusted Cases | Yes
Seasonal Amplitude | Yes
Peak Month | Yes
Trough Month | Yes
Set the Description property on every measure as you go | Yes |  | It is the tooltip a report author sees. Written at the end, it gets skipped.
Commit the .dax files to dax/ | Yes |  | One file per display folder.
PHASE 6 — VALIDATION (document 02 §9)
Run all seventeen pre-publication checks | Yes |  | Not a subset. The cases-versus-dollars check is the one that matters most.
Record the results in docs/22_Validation_Results.xlsx with a date | Yes |  | Document 22, Check Results tab — one row per check. The Run Summary tab counts the run for you. Makes the numbers reproducible rather than merely present.
Re-run validation after any fact-table reload | Yes |  | Recurring, not one-off.
PHASE 7 — PUBLISH AND BIND (document 02 §10)
Save the model as RetailEconomics_Model.pbip inside pbip/ | Yes |  | One blank page. This file is a model, not a report.
Publish the semantic model to the Pro workspace | Yes |  | Once, before any report is started.
Map the SQL Server source to the gateway | Yes |  | Windows or SQL authentication.
Map api.census.gov and fred.stlouisfed.org as Anonymous | Yes |  | These do not route through the gateway.
Enter the Census API key as a Service credential | Yes |  | Never travels with the reports.
Set the refresh schedule (twice weekly is sufficient) | Yes |  | MARTS advance estimates arrive mid-month; the county file updates monthly.
Deployment pipelines (Dev/Test/Prod) | No | N/A | Requires Premium or Fabric capacity. One workspace is the scope.
Publish as a Power BI App | No | N/A | Audience is a reviewer following a link, not an organisation.
PHASE 8 — REPORTS (document 15) |  |  | Build the reports in parallel so components can be built once and copied over
Apply the report theme BEFORE the first visual — R1 | Yes |  | A theme changes defaults; it does not overwrite what is already set by hand.
Apply the report theme BEFORE the first visual — R2 | Yes
Apply the report theme BEFORE the first visual — R3 | Yes
Build the shared header band once and copy it to every page | Yes |  | Doc 15 §3.2.
Sync the date slicer within each report | Yes |  | Do not sync the category, item-type or supplier slicers.
Build R1 — three pages, specs 1 to 3 | Yes
Build Page 1 - | Yes
Build Page 2 - | Yes
Build Page 3 - | Yes
Build R2 — three pages, specs 4 to 6 | Yes
Build Page 1 - | Yes
Build Page 2 - | Yes
Build Page 3 - | Yes
Build R3 — four pages, specs 7 to 10 | Yes
Build Page 1 - | Yes
Build Page 2 - | Yes
Build Page 3 - | Yes
Setup and initialize Cross-Report Wiring | Yes
Sync Slicers | Yes
Reset bookmarks | Yes
Create drillthrough pages | Yes
Setup drillthrough | Yes
Create tooltip pages | Yes
Setup tooltips | Yes
Verify all 87 visuals against the doc 15 spec tables | Yes |  | Type, fields, position and formatting.
Add the stated caveats as text boxes (2017 cohort, seasonality method) | Yes |  | The caveat is part of the specification, not decoration.
Confirm no measure was created inside a report file | Yes |  | A report-level measure exists in one report only — the divergence the architecture prevents.
Accessibility pass: alt text, tab order, contrast | Yes |  | Cheap to do, and a reviewer notices its absence.
Publish R1, R2 and R3 to the workspace | Yes |  | Each separately, after it is built.
Mobile layouts | No | N/A | Reviewed on a desktop. A mobile layout for ten dense pages is work with no audience here.
Usage metrics / audience analytics | No | N/A | No recurring audience to measure.
PHASE 9 — PACKAGING (document 00 §11, §13, §14)
Save all four .pbip files inside pbip/ and commit the TMDL | Yes |  | At least one commit must show a readable measure diff.
Commit the four .pbix binaries to pbix/ at milestone | Yes |  | What a reviewer double-clicks.
Capture eleven screenshots at 1280 x 720 into assets/ | Yes |  | Ten report pages plus the model view.
Capture one screenshot of a PBIP commit diff | Yes |  | The strongest "works like an engineer" image the project can carry.
Write the root README with the images and the limitations | Yes |  | Doc 00 §13. The limitations paragraph belongs on the landing page.
Run the doc 00 §14 verification checklist end to end | Yes |  | Including the repository search for ".csv" and "key=" returning zero hits.
Confirm the repository contains no data file and no credential | Yes |  | If a key was ever committed, regenerate it — deletion does not remove it from history.